## User Registration
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_UR_01 | Register with all valid mandatory fields | Fill all required fields and submit | Success message shown | Registration success message shown | Positive | High | PASS
TC_UR_02 | Password and confirm password do not match | Fill mismatched passwords | Error: "Passwords did not match" | Error shown: "Passwords did not match" | Negative | High | PASS
TC_UR_03 | Submit with blank required fields | Leave First/Last Name empty | Validation errors shown | Field-level error: "First name is required" | Negative | High | PASS
TC_UR_04 | Use already existing username | Use same username twice | Error: "Username already exists" | Error shown: "This username already exists" | Negative | High | PASS
TC_UR_05 | Long strings in name fields | Enter 100+ characters | Should be trimmed or blocked | Registration successful; no truncation | Boundary | Medium | PASS
TC_UR_06 | Special characters in name fields | Enter @#$ in First/Last name | Validation error shown | Allowed; no error shown | Negative | Medium | FAIL
TC_UR_07 | Alphabets in ZIP code | Enter abcd in ZIP | Validation error shown | Form accepts alphabetic ZIP | Negative | Medium | FAIL
TC_UR_08 | Short password (2 characters) | Enter 12 as password | Minimum password length error | Registration successful | Negative | Medium | FAIL
TC_UR_09 | Password fields masked | Observe during input | Fields should show dots/stars | Both fields are masked | UI/Functional | Low | PASS
TC_UR_10 | Leading/trailing spaces in username | Enter nithish123 | Should be trimmed or error shown | Spaces accepted in username | Functional | Low | FAIL
TC_UR_11 | Numbers only in username | Enter 12345678 | Should allow registration | Registration successful | Positive | Medium | PASS
TC_UR_12 | Mixed case password | Enter Parabank123 in both fields | Should allow registration | Registration successful | Positive | Medium | PASS
TC_UR_13 | Blank confirm password | Leave confirm password empty | Error: "Passwords did not match" | Error shown | Negative | High | PASS
TC_UR_14 | Leave address field blank | Fill all except address | Registration successful | Registration successful | Positive | Low | PASS
TC_UR_15 | Disable JavaScript and register | Submit form without JS | Should work server-side | Form submitted successfully | Functional | Medium | PASS

## Login
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_LG_01 | Login with valid username and password | Enter correct credentials and click Login | User is redirected to account overview | Login successful, account dashboard shown | Positive | High | PASS
TC_LG_02 | Login with incorrect password | Enter valid username and wrong password | Error message shown: "The username and password could not be verified" | Error shown as expected | Negative | High | PASS
TC_LG_03 | Login with blank username | Leave username empty | Error message shown | Error shown: "Please enter a username" | Negative | High | PASS
TC_LG_04 | Login with blank password | Leave password field empty | Error message shown | Error shown: "Please enter a password" | Negative | High | PASS
TC_LG_05 | Login with both fields blank | Leave both username and password empty | Error shown | Error shown: "Please enter a username" | Negative | High | PASS
TC_LG_06 | Login with invalid special characters | Use #$%@ in username and password | Error shown | Error shown as expected | Negative | Medium | PASS
TC_LG_07 | Login with only spaces in username and password | Enter space characters only | Should show validation error | Treated as invalid; error shown | Negative | Medium | PASS
TC_LG_08 | Login with long inputs (100+ characters) | Input extremely long strings | Should show error or truncate | Still shows error: login failed | Boundary | Medium | PASS
TC_LG_09 | Login with leading/trailing spaces | Enter username and correct password | Spaces should be trimmed automatically | Login fails; spaces are not trimmed | Negative | Low | FAIL
TC_LG_10 | Login with username in uppercase/lowercase | Enter correct username but change case | Should be case-insensitive | Login fails (username is case-sensitive) | Functional | Medium | FAIL
TC_LG_11 | Login with correct password and invalid username | Wrong username, correct password | Error message shown | Login fails; error shown | Negative | High | PASS
TC_LG_12 | Copy-paste credentials and login | Paste valid credentials instead of typing | Login should succeed | Login successful | Positive | Medium | PASS
TC_LG_13 | Navigate to another page and go back after login | Login → Navigate → Back button | User should stay logged in | User session retained | Positive | Low | PASS
TC_LG_14 | Refresh page after failed login | Enter invalid credentials → Refresh | Login fields should reset | Fields reset; error gone | Functional | Low | PASS
TC_LG_15 | Try login after session timeout (simulate wait) | Login → Wait 15+ min → Try accessing again | Session timeout; forced logout | Still logged in — session not expired | Functional | Medium | FAIL

## Logout
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_LO_01 | Verify successful logout | Login → Click on Logout | Redirected to login page with no error | User redirected to login page | Positive | High | PASS
TC_LO_02 | Verify user cannot access dashboard after logout | Login → Logout → Manually go to /overview.htm | Should be redirected to login page (session cleared) | User redirected to login page | Negative | High | PASS
TC_LO_03 | Verify browser back button after logout | Login → Logout → Press browser Back | Should not access account pages | Back button returns to login page; dashboard not shown | Negative | Medium | PASS
TC_LO_04 | Verify logout ends session properly on multiple tabs | Login → Open dashboard in new tab → Logout in original tab → Refresh new tab | New tab should ask for login | New tab forces login after logout | Functional | Medium | PASS

## Open New Account
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_ONA_01 | Open new account with default options | Go to “Open New Account” → Click Submit | Account created, account number shown | Account successfully created | Positive | High | PASS
TC_ONA_02 | Open account with “Savings” account type selected | Select Savings → Submit | Savings account created | Savings account created | Positive | Medium | PASS
TC_ONA_03 | Open account with “Checking” account type selected | Select Checking → Submit | Checking account created | Checking account created | Positive | Medium | PASS
TC_ONA_04 | Don’t select account type or funding account | Leave both dropdowns unselected | Error: Required selection | Form still submits and creates default account | Negative | Medium | FAIL
TC_ONA_05 | Try creating multiple accounts back-to-back | Submit form multiple times quickly | All accounts created without error | Multiple accounts created | Boundary | Low | PASS
TC_ONA_06 | Open account from zero balance source account | Use a funding account with no balance | Error or warning shown | Account still created — no validation | Negative | Medium | FAIL
TC_ONA_07 | Verify account creation reflects in Accounts Overview | Create new account → Navigate to Accounts Overview | Newly created account should be listed | Account appears in overview with balance | Integration | High | PASS
TC_ONA_08 | Attempt to create account using same funding account repeatedly | Select same funding account and open 3+ new accounts quickly | Each account created independently | All accounts created successfully | Boundary | Medium | PASS
TC_ONA_09 | Verify balance remains same in funding account after account creation | Note balance → Create account using it → Check balance again | Funding account balance remains unchanged (no funds moved) | Balance remains same (no deduction) | Business Logic | Medium | PASS
TC_ONA_10 | Check session expiry handling during account creation | Login → Wait 10–15 min idle → Try to create new account | Session should expire or redirect to login page | Redirects to login page (session expired) | Security | Medium | PASS

## Account Overview
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_AO_01 | View accounts after login | Login → Click Accounts Overview | List of accounts with balances shown | Accounts and balances displayed | Positive | High | PASS
TC_AO_02 | Click account number to view transaction history | Click any account number from the list | Redirected to transaction history of that account | Redirect works correctly | Positive | High | PASS
TC_AO_03 | Verify total balance calculation | Manually sum balances of all listed accounts → Compare with total shown | Total balance should match | Total displayed correctly | Functional | Medium | PASS
TC_AO_04 | Check layout when multiple accounts exist | Create 3+ accounts → Go to Accounts Overview | All accounts displayed cleanly | Layout supports multiple accounts well | UI | Medium | PASS
TC_AO_05 | Verify accounts are sorted or listed by creation order | Create accounts one-by-one → Check their order on Accounts Overview | Accounts listed in order of creation or sorted logically | Order is maintained as expected | UI/Functional | Low | PASS
TC_AO_06 | Click each account link to verify redirection | Click on each account in the overview | Each click should open the respective account detail page | Navigation works correctly | Navigation | Medium | PASS
TC_AO_07 | Check responsiveness/layout with 5 or more accounts | Create 5+ accounts → Go to Accounts Overview | Page remains user-friendly and readable | Layout remains aligned and clear | UI/Boundary | Low | PASS

## Fund Transfer
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_FT_01 | Transfer valid amount between two accounts | Enter valid amount and select From/To accounts, then submit | Transfer successful message shown | Transfer completes, balance updates shown | Positive | High | PASS
TC_FT_02 | Transfer amount greater than available balance | Try transferring $500 when only $200 available | Error: Insufficient funds | Transfer still succeeds, source account becomes negative | Negative (logic) | High | FAIL
TC_FT_03 | Transfer with negative amount | Enter -500 in the amount field | Validation error should be shown | Transfer still completes; both accounts updated | Negative (bug) | High | FAIL
TC_FT_04 | Transfer with zero amount | Enter 0 as the amount | Error: Invalid amount | Transfer completes with $0 | Negative | Medium | FAIL
TC_FT_05 | Leave amount field blank | Submit without entering amount | Error message shown | Field-level error shown | Negative | Medium | PASS
TC_FT_06 | Use non-numeric characters in amount field | Enter abc or !@# as amount | Validation error should appear | Form accepts input but transfer fails silently | Negative (UI) | Medium | FAIL
TC_FT_07 | Select same account in From and To fields | Choose the same account in both dropdowns | Error: Cannot transfer to same account | Transfer completes successfully | Negative (logic) | Medium | FAIL
TC_FT_08 | Submit with no accounts selected | Leave From/To account blank | Validation error shown | Error shown | Negative | Medium | PASS
TC_FT_09 | Enter amount with decimal value | Enter 123.45 as amount | Transfer completes with exact decimal value | Transfer successful | Positive | Medium | PASS
TC_FT_10 | Verify balance update in source and destination after transfer | Note balances before and after successful transfer | Source debited, destination credited | Both balances updated correctly | Functional | High | PASS
TC_FT_11 | Check transaction log after successful transfer | Perform transfer, then go to “Accounts → Transaction” page | Transaction entry visible | Transfer log entry is shown | Functional/History | Medium | PASS
TC_FT_12 | Refresh page after transfer without submitting again | Submit transfer → Refresh page | Should not duplicate the transaction | No duplication | Functional | Low | PASS

## Bill Payments
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_BP_01 | Pay bill with valid payee info and amount | Enter all required fields and valid amount, click Send Payment | Payment successful confirmation shown | Payment success message displayed | Positive | High | PASS
TC_BP_02 | Leave all fields blank and submit | Click Send Payment without entering anything | Validation errors for all required fields | Errors shown for missing fields | Negative | High | PASS
TC_BP_03 | Enter invalid characters in payee name and address | Use @#$% or numeric-only names | Validation error shown | Payment still proceeds | Negative | Medium | FAIL
TC_BP_04 | Enter negative payment amount | Input -500 in the amount field | Error message: amount must be positive | Payment succeeds with negative amount | Negative | High | FAIL
TC_BP_05 | Enter amount greater than available balance | Pay $1000 from account with only $500 | Error: Insufficient funds | Payment succeeds, account shows negative balance | Negative | High | FAIL
TC_BP_06 | Enter alphanumeric string in amount field | Input abc123 in amount | Validation error shown | No error shown; unclear behavior | Negative | Medium | FAIL
TC_BP_07 | Try submitting form with only payee name filled | Fill only payee name and click Send Payment | Error shown for missing required fields | Errors shown | Negative | Medium | PASS
TC_BP_08 | Select different accounts for payment | Choose different From Account options | Payment should proceed | Payment successful | Positive | Medium | PASS
TC_BP_09 | Submit decimal value in amount field | Enter amount like 123.45 | Payment succeeds and reflects correct amount | Works as expected | Positive | Medium | PASS
TC_BP_10 | Check balance after successful bill payment | Note balance before and after payment | Balance deducted by payment amount | Balance correctly updated | Functional | High | PASS

## Request loan
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_RL_01 | Request loan with valid inputs | Enter valid loan amount, down payment, and select account | Loan request accepted; confirmation shown | Loan approved message shown | Positive | High | PASS
TC_RL_02 | Submit loan request with blank fields | Leave loan amount and down payment blank | Validation errors should be shown | Error shown for missing values | Negative | High | PASS
TC_RL_03 | Request with loan amount less than down payment | Loan = 500, Down Payment = 1000 | Error message should appear | Request still accepted | Negative | Medium | FAIL
TC_RL_04 | Request with negative loan amount | Enter -1000 as loan amount | Validation error should be shown | Loan processed with negative value | Negative | High | FAIL
TC_RL_05 | Use characters in amount/down payment fields | Input abcd or 12abc | Error message should appear | Fields accept alphanumeric input, no error | Negative | Medium | FAIL
TC_RL_06 | Use decimal values in loan amount and down payment | Enter 1000.50 and 500.25 | Loan request should process correctly | Loan approved with exact decimal values | Positive | Medium | PASS
TC_RL_07 | Submit loan request without selecting an account | Leave "From Account" unselected | Error shown or dropdown should be required | Loan request blocked, error shown | Negative | Medium | PASS
TC_RL_08 | Request large loan (e.g., 100000) to test system handling | Enter high loan amount | Should either approve, deny, or show error | Loan request approved | Boundary | Medium | PASS

## Transaction History
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_TH_01 | View transaction history after successful fund transfer | Make a transfer → Click account number → View recent transactions | Recent transaction entry should appear at top | Entry appears as expected | Positive | High | PASS
TC_TH_02 | View transaction after bill payment | Pay bill → Open transaction history | Bill payment transaction should be logged | Bill Pay transaction appears | Positive | High | PASS
TC_TH_03 | Check history with no transactions | Use a new account with no activity | Should show message like "No transactions available" | Page is blank (no message shown) | Negative | Medium | FAIL
TC_TH_04 | Verify filter by transaction type | Use dropdown to filter by “Credit”, “Debit”, etc. | Only matching transactions should be shown | Filters not working — all transactions shown | Functional | Medium | FAIL
TC_TH_05 | Click on transaction link (if available) | Click on transaction ID/description if clickable | Should open detailed view (if supported) | No clickable links — static only | UI/Functional | Low | PASS
TC_TH_06 | Validate transaction amount and balance columns | Compare credited/debited values vs current balance | Accurate amounts reflected | All amounts displayed correctly | Functional | High | PASS

## Contact us
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_CF_01 | Submit contact form with all valid inputs | Enter name, email, phone, and message → Submit | Message should be sent successfully or confirmation shown | Form submits, no confirmation message shown | Positive | Medium | PASS
TC_CF_02 | Submit with all fields blank | Click Submit without entering anything | Error messages shown for required fields | No client-side validation shown; blank form still submits | Negative | High | FAIL
TC_CF_03 | Use invalid email format | Enter email like abc@ or test.com | Error shown for invalid email format | No validation; form accepts invalid email | Negative | Medium | FAIL
TC_CF_04 | Use special characters in name/phone fields | Enter @#$$% in name and phone | Error message shown | No validation; form still submits | Negative | Low | FAIL
TC_CF_05 | Submit form with a very long message (>1000 characters) | Paste large message in the Message box | Should accept up to max limit or show truncation | Form accepts long message | Boundary | Low | PASS
TC_CF_06 | Leave phone number blank | Fill all except phone number and submit | Form should still submit (optional field) | Form submits successfully | Positive | Low | PASS

## Find Transactions
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_FT_01 | Search by exact transaction ID | Enter valid transaction ID and click Find | Specific transaction should be shown | Correct transaction is shown | Positive | High | PASS
TC_FT_02 | Search using invalid/nonexistent transaction ID | Enter random ID like 9999999 | No results should be found; show “No transaction found” | Shows empty result as expected | Negative | Medium | PASS
TC_FT_03 | Search transactions by date range | Enter From Date and To Date (e.g., last 7 days) | Only transactions in that range should appear | All transactions appear — filter not applied | Functional | High | FAIL
TC_FT_04 | Search by transaction amount | Enter an exact amount like 200 | Only matching amount transactions should be listed | Filter not applied — shows all transactions | Negative | Medium | FAIL
TC_FT_05 | Submit without entering any search criteria | Click Find button with all fields blank | All transactions shown or prompt to enter search field | All transactions displayed | Functional | Low | PASS
TC_FT_06 | Use invalid date format | Enter invalid date like abcd or 2025-15-99 | Validation error should be shown | No validation; silently reloads or breaks silently | Negative | Medium | FAIL

## Update Contact Info
Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Type | Priority | Result
TC_UC_01 | Update all fields with valid data | Fill new values in address, city, state, zip, phone, then click update | Info updated and confirmation shown | Form redirects with updated data shown | Positive | High | PASS
TC_UC_02 | Leave all fields blank and click update | Submit without filling anything | Error message shown for required fields | No errors; update accepted with blank data | Negative | High | FAIL
TC_UC_03 | Use special characters in city/state fields | Enter @#!$ or 12345 in city/state | Validation error should appear | Form accepts and updates values | Negative | Medium | FAIL
TC_UC_04 | Use alphabets in phone/zip fields | Enter abcd in phone or zip code | Validation error should appear | Form accepts and updates non-numeric phone/zip | Negative | Medium | FAIL
TC_UC_05 | Input valid long address (100+ characters) | Enter long text in address field | Should accept or trim long string | Long address accepted and saved | Boundary | Low | PASS
TC_UC_06 | Update phone number only and submit | Modify just phone field → click update | Only phone gets updated; others remain unchanged | Phone field updated correctly | Positive | Medium | PASS
TC_UC_07 | Update only City and submit | Change just the City field → Click Update Profile | City is updated successfully, other fields remain unchanged | City updated successfully | Functional | Medium | PASS
TC_UC_08 | Update contact info with minimum valid ZIP (e.g., 5-digit) | Enter ZIP as 12345 along with valid values in other fields | ZIP accepted, info updated | ZIP accepted, info updated | Boundary | Medium | PASS
TC_UC_09 | Enter alphanumeric address and update | Use address like 22B Baker Street | Address updated successfully | Form accepts and saves alphanumeric address | Functional | Low | PASS
TC_UC_10 | Verify persistence after updating contact info and logging out | Update details → Logout → Login again → Check contact info | Previously updated info should persist | Data saved and persists | Positive | Medium | PASS